## Risk Register
Risk ID | Risk Description | Category | Probability | Impact | Risk Level | Mitigation Strategy | Risk Owner | Status
R-001 | AI generates inaccurate responses | Technical | Medium | High | High | Use approved knowledge base and periodic evaluation | AI Team | Open
R-002 | Sensitive customer data exposure | Security | Low | High | High | Encrypt data and enforce access controls | Security Lead | Open
R-003 | Knowledge base becomes outdated | Operational | Medium | Medium | Medium | Schedule regular reviews | Knowledge Manager | Open
R-004 | High response latency | Performance | Medium | High | High | Monitor and optimize infrastructure | Engineering | Open
R-005 | Failure to escalate complex issues | Operational | Low | High | Medium | Test escalation logic | Support Lead | Open
R-006 | Third-party API outage | External | Medium | High | High | Fallback procedures | Engineering | Open
R-007 | Low user adoption | Business | Low | Medium | Low | Collect user feedback | Product Owner | Open
R-008 | Prompt injection attacks | Security | Medium | High | High | Input validation and AI guardrails | AI Team | Open
R-009 | Scope creep | Project | Medium | Medium | Medium | Formal change control | Project Manager | Open
R-010 | Bias in AI responses | AI Ethics | Low | High | Medium | Bias testing and monitoring | AI Team | Open